## Slide 1
Bridge
Project Planning and Estimation
Between Ch 19 and Ch 20
AI-Driven SDLC — A Federated Framework

## Slide 2
Learning Objectives
Bridge — Project Planning and Estimation
Apply three-point estimation (best, most likely, worst case)
Distinguish p50 commitments from p80 commitments and their consequences
Manage buffer at the right level of aggregation
Distinguish schedule slippage from scope drift; apply different remedies

## Slide 3
Why Estimation Is Hard
Bridge
Cone of uncertainty: estimates early in a project are widely uncertain
Planning fallacy: humans are systematically optimistic
Tail risk: low-probability long-tail events skew the average
Three-point estimation captures all three

## Slide 4
p50 vs. p80 Commitments
Bridge
p50 (most likely): late roughly half the time — fails at coin-flip rate
p80: late roughly one in five times
External commitments at p80 protect the customer relationship
Internal stretch goals at p50 are fine — they're different from external commitments

## Slide 5
Buffer Discipline
Bridge
Buffer at the team level, not hidden in individual task estimates
Buffer that's named is buffer that can be defended; buffer hidden in task estimates evaporates
When something slips, the buffer is what protects the commitment
A team without named buffer is a team committing at p50

## Slide 6
Slippage vs. Drift
Bridge
Schedule slippage: the work is taking longer than estimated; work itself is what was specified
Scope drift: the work is more than originally specified
Adding capacity to slipping project: sometimes works (with caveats)
Adding capacity to drifted project: makes it worse — the new capacity does new scope

## Slide 7
Common Mistakes
Bridge — patterns that look reasonable and aren't
Committing externally at p50
Hiding buffer inside individual task estimates
Adding capacity to a slipping project (Brooks's law)

## Slide 8
Takeaway
Bridge — Project Planning and Estimation
Estimation is hard because the future is uncertain; the discipline is to make uncertainty explicit. Commit externally at p80, name buffer at the team level, distinguish slippage from drift. Honest replanning beats death-march compression.